## Testing record
ID | Component_Tested | Testing_Objective | Scenario | Expected | Actual | Pass_Fail | Issue_Identified | Action_Taken | Retest_Result | Collaborating_Track | Evidence
T01 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Reproduce Week 6 candidate (CV and hold-out) | CV AUC 0.514 and hold-out AUC 0.529 (±0.002) | CV AUC 0.514; hold-out AUC 0.529 | PASS |  |  |  | Data Science | notebook B1
T02 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Stability across 30 random splits | AUC > 0.5 in ≥ 90% of splits (C4) | 40% above 0.5; mean 0.495 (range 0.461–0.549) | FAIL | Skill is not consistently above chance |  |  | Data Science | Fig. w01
T03 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Time-based split (train Jan–Sep, test Oct–Dec) | AUC > 0.5 with CI above 0.5 (C4, C2) | AUC 0.480 (95% CI 0.433–0.528) | FAIL | CI includes 0.5: no demonstrable skill on future data |  |  | Data Science | Fig. w01
T04 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Metrics at deployable thresholds on untouched hold-out | Top-20% rule has lift ≥ 1.5 over prevalence (C3) | Lift 1.42x (precision 0.167 vs prevalence 0.117); 0.5 threshold flags 0 patients; F1-optimal threshold flags 985 of 1000 | FAIL | At 0.5 the model never flags anyone; the F1-optimal threshold flags nearly everyone — the model has no useful operating point |  |  | Data Science | table t_metrics_candidate_holdout.csv; Fig. w02
T05 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Calibration (out-of-fold, all encounters) | Calibration slope within 0.8–1.2 (C5) and Brier below baseline | Slope 0.18 (95% CI -0.06–0.41); Brier 0.1043 vs baseline 0.1035 | FAIL | Predicted risks are not informative about actual risk (slope far below 1; Brier no better than baseline) |  |  | Data Science | Fig. w03
T06 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Error analysis: FN vs TP and FP vs TN profiles; do flags enrich for admissions? | Errors show outcome-related, correctable patterns, and flagged patients are admitted more often than unflagged | Flagged patients are admitted at 12.7% vs 11.5% unflagged (p = 0.31); 78% of admissions missed, 87% of flags false alarms. Profile differences (9 of 16 and 13 of 16 variables after Holm) mirror the features the score is built from (selection effect), led by DepartmentName/DayOfWeek/ProvinceName - categories with no demonstrated link to admission | FAIL | Flags are driven by noise categories, not by outcome-related patterns; there is no error pattern that feature fixes could remove |  |  | Data Science | table t_error_profile_tests.csv
T07 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Performance across segments (gender, age band, province, department, visit type, severity, chronic status) | AUC consistently > 0.5 across segments; no segment where the model fails | 34 segments: AUC 0.37–0.59; 3 intervals above and 1 below 0.5 (≈1.7 expected by chance); 0 significant after Holm correction | FAIL | No segment where the model works reliably once multiple testing is accounted for; results scatter around 0.5 |  |  | Data Science | Fig. w04; table t_segment_auc.csv
T08 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Overfitting: train vs CV AUC; learning curve | Small train–CV gap and CV AUC rising with more data | Candidate gap 0.081 (train 0.601, CV 0.520); learning-curve train AUC falls 0.78→0.61 while CV stays ~0.5; unconstrained forest train 1.000 vs CV 0.499 | FAIL | Mild overfitting (train above CV) and no learning: CV AUC stays at ~0.5 as data grows while training AUC falls — the model fits noise. Flexible models only memorise it |  |  | Data Science | Fig. w05; table t_overfitting.csv
T09 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Feature validity: per-fold permutation importance and prediction-time availability | Some features contribute consistently; all features available at prediction time | 1 of 18 features consistent across folds (≈0.6 by chance); max importance 0.0051; one mild look-ahead feature found (PatientVisits) | FAIL | No feature contributes reliably; PatientVisits uses the full-year count (look-ahead) — must be 'visits before this appointment' in production | Documented in feature-timing audit and the input contract |  | Data Science | Fig. w06; tables t_feature_importance_folds.csv, t_feature_timing_audit.csv
T10 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Negative control (shuffled labels) | Mean AUC ≈ 0.50 (pipeline free of leakage/bias) | Shuffled mean 0.501 (sd 0.018); observed 0.520, permutation p = 0.19 | PASS |  |  |  | Data Science | notebook D4
T11 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Planted-signal detection (can the method find a real effect?) | Pipeline recovers a planted Age effect and flags it significant | Detected from true AUC ≈ 0.57 upward; with no planted effect, no detection | PASS |  |  |  | Data Science | Fig. w06; table t_planted_signal_power.csv
T12 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Refinement comparison on development CV (7 variants vs candidate) | At least one refinement beats the candidate by ≥ 0.02 AUC (corrected-t p < 0.05) | Best: R1 Clinical-core features, ΔAUC +0.019 (p = 0.13); R5 calibration changes Brier -0.0013 | FAIL | No refinement produced a meaningful improvement | Refinements tried: clinical-core features, L2/L1 regularisation, class weights, shallow boosting, isotonic calibration |  | Data Science | Fig. w07; table t_refinement_dev_cv.csv
T13 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Re-test of refined model on untouched hold-out | Refined AUC ≥ 0.65 with lower CI bound > 0.5 (C1, C2) | R1 Clinical-core features: AUC 0.537 (95% CI 0.48–0.59); candidate 0.529; paired Δ +0.008 (95% CI -0.040 to +0.060) | FAIL | Refinement does not create skill |  |  | Data Science | Fig. w07
T14 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Re-test: stability and time-based split of refined model | AUC > 0.5 in ≥ 90% of splits and in the time split (C4) | 63% of splits above 0.5 (mean 0.514); time split 0.488 (CI 0.44–0.53) | FAIL |  |  |  | Data Science | notebook E
T15 | Week 6 candidate admission classifier | Determine whether the model meets the pre-registered acceptance criteria | Re-test: calibration after refinement (slope; isotonic recalibration) | Slope within 0.8–1.2 and Brier below baseline (C5) | Refined slope 0.24, Brier 0.1037; isotonic-calibrated candidate Brier 0.1037 vs baseline 0.1035 | FAIL | Recalibration can only push predictions toward the average rate (Brier ≈ baseline); it cannot add information |  |  | Data Science | notebook E
X01 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Valid single record | Returns one probability in [0, 1] | V1: scored, p=0.089 | PASS |  |  | V2: PASS - scored, p=0.089 | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X02 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Valid batch of 200 | 200 finite probabilities | V1: 200 finite scores | PASS |  |  | V2: PASS - 200 finite scores | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X03 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Columns in a different order | Identical scores (columns matched by name) | V1: identical scores | PASS |  |  | V2: PASS - identical scores | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X04 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Unexpected extra column (e.g. PatientName) | Scored; ignored column reported (identifier safety) | V1: scored silently; extra column (possible identifier) not reported | FAIL | Week 6 scoring behaviour does not meet the interface contract | Report extra columns (possible identifiers) in the output warnings | V2: PASS - scored and extra column reported | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X05 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Required column missing (Age) | Clear error naming 'Age' | V1: ValueError: columns are missing: {'Age'} | PASS |  |  | V2: PASS - ScoringError: Missing required column(s): ['Age'] | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X06 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Unseen category in an open field (Occupation = Astronaut) | Scored, and the unseen value is reported | V1: scored silently; unseen category not reported | FAIL | Week 6 scoring behaviour does not meet the interface contract | Flag categories never seen in training instead of scoring silently | V2: PASS - scored with warning | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X07 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Impossible value in a closed list (ProvinceName = Mars) | Rejected with an error naming ProvinceName | V1: scored an impossible province without complaint | FAIL | Week 6 scoring behaviour does not meet the interface contract | Closed lists (province, gender, chronic condition) enforced | V2: PASS - ScoringError: Column 'ProvinceName' has value(s) outside the allowed list ['Eastern', 'Kigali City', 'Northern | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X08 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Out-of-range numbers (Age = -5, BMI = 500) | Rejected with an error naming the column | V1: scored Age=-5, BMI=500 without complaint | FAIL | Week 6 scoring behaviour does not meet the interface contract | Numeric range checks from the contract | V2: PASS - ScoringError: Column 'Age' out of allowed range [0, 110] at row(s) [0] | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X09 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Missing numeric value (Age = NaN) | Clear error naming 'Age' | V1: ValueError: Input X contains NaN. LogisticRegression does not accept missing values encoded as NaN natively. F | FAIL | Week 6 scoring behaviour does not meet the interface contract | Missing values rejected with the field name | V2: PASS - ScoringError: Column 'Age' has missing value(s) at row(s) [0]; missing values are not imputed | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X10 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Wrong data type (Age = 'forty') | Clear error naming 'Age' | V1: ValueError: could not convert string to float: 'forty' | FAIL | Week 6 scoring behaviour does not meet the interface contract | Type checks with the field name | V2: PASS - ScoringError: Column 'Age' must be numeric; non-numeric value(s) at row(s) [0] | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X11 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Empty input (0 rows) | Empty result, no crash | V1: ValueError: Found array with 0 sample(s) (shape=(0, 7)) while a minimum of 1 is required by StandardScaler. | FAIL | Week 6 scoring behaviour does not meet the interface contract | Empty input returns an empty, correctly-typed result | V2: PASS - empty result | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X12 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Determinism (same input twice) | Identical output | V1: identical on repeat | PASS |  |  | V2: PASS - identical on repeat | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X13 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Persistence (save and reload the scorer) | Identical output after reload | V1: identical after save/load | PASS |  |  | V2: PASS - identical after save/load | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X14 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: ChronicCondition = 'None' (valid: no chronic disease) | Accepted as a normal value | V1: 'None' accepted as a value | PASS |  |  | V2: PASS - 'None' accepted as a value | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X15 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: ChronicCondition missing — the CSV 'None'→NaN pitfall | Rejected with a clear error naming ChronicCondition | V1: TypeError: ufunc 'isnan' not supported for the input types, and the inputs could not be safely coerced to any supported | FAIL | Week 6 scoring behaviour does not meet the interface contract | Missing ChronicCondition rejected with a hint about the CSV 'None' pitfall | V2: PASS - ScoringError: Column 'ChronicCondition' has missing value(s) at row(s) [0] - if the data came from a CSV, the text 'None | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X16 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Output schema | risk_score, risk_band, warnings, model_version, use_caution | V1: bare array: no band, warnings, version or caution flag | FAIL | Week 6 scoring behaviour does not meet the interface contract | Documented output schema incl. risk band, version and 'use caution' field | V2: PASS - output schema as documented | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X17 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Input is not a DataFrame | Clear error saying a DataFrame is required | V1: ValueError: Expected 2D array, got scalar array instead: array={'Age': 12, 'BMI': 43.3, 'RiskScore': 2, 'Docto | FAIL | Week 6 scoring behaviour does not meet the interface contract | Explicit DataFrame requirement | V2: PASS - ScoringError: Input must be a pandas DataFrame with one row per appointment. | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv
X18 | Scoring interface (Week 6 model wrapper) | Determine whether the interface handles valid, invalid and edge-case inputs per the contract | Interface: Speed: 10,000 rows | Under 5 seconds | V1: 10,000 rows in 0.02s | PASS |  |  | V2: PASS - 10,000 rows in 0.02s | ML Engineering (interface contract; teammate sign-off pending) | src/admission_risk_scorer.py; table t_scoring_interface_tests.csv

## Integration & issue log
ID | Issue | Severity | Found in | Status | Owner | Action / mitigation | Retest
I-01 | Candidate admission model has no predictive skill (hold-out AUC 0.529, CI includes 0.50; 0 of 6 acceptance criteria met) | Critical | Testing T02–T15 | Open — cannot be fixed with this data | Data Science | Do not use for patient-level decisions; keep rule-based risk list; revisit after Week 8 data additions | Re-tested after 7 refinements: no improvement (T12–T15)
I-02 | Brief assumes a missed-appointment (no-show) model on HealthConnect_Appointment_Data.csv; project data contain no attendance field | Critical (dependency) | Week 6→7 transition | Open — needs decision | Project Management / Data owner | Obtain the appointment/attendance extract or confirm the admission model as the agreed proxy; re-use this test harness on the new target | n/a
I-03 | Week 6 scoring interface (V1) accepted impossible values, missing fields and unreported extra columns; returned a bare array (10 of 18 interface tests failed) | High | Interface tests X01–X18 | Resolved | Data Science → ML Engineering | Input/output contract, validation layer, documented output schema (V2) | V2 passes 18/18
I-04 | CSV 'None' (no chronic disease) is read as missing by default; V1 silently scored it as a category | Medium | X14, X15 | Resolved (guard in V2); recurring risk | Data Science / ML Engineering | V2 rejects missing ChronicCondition with a hint; read CSVs with keep_default_na=False | X15 PASS in V2
I-05 | PatientVisits counts the whole year, so it includes visits after the one being scored (mild look-ahead) | Medium | T09 / feature-timing audit | Open | Data Science / ML Engineering | Recompute as 'visits before this appointment date' in the production pipeline | Not re-tested (no signal either way)
I-06 | Diagnosis, severity, labs, prescriptions and referral are only known after the visit (leakage if used at booking time) | Medium | Feature-timing audit | Resolved | Data Science | Excluded from the deployed feature set; documented in model card | n/a
I-07 | Predicted probabilities are uninformative (calibration slope 0.18; Brier 0.1043 vs baseline 0.1035) | High | T05, T15 | Open — cannot be fixed with this data | Data Science | Do not display risk percentages; recalibration cannot add information | Isotonic calibration: Brier 0.1037 (baseline 0.1035)
I-08 | Facility, department and doctor keys are inconsistent in the source data (carried from Week 6); only 5,000 of 60,000 billed visits have an appointment record | High | Week 6 data-quality report | Open | Project Management / Data owner | Re-extract appointments with enforced foreign keys before any facility-level modelling | n/a
I-09 | Only 12 months of data; the time-based test has 1235 appointments and 162 admissions | Medium | T03 | Open | Data Science | Collect 24+ months; repeat the time-based test | n/a
I-10 | ML Engineering teammate has not yet run the hand-off tests or signed off the contract | Medium | Cross-track record | Open | Intern + ML Engineering teammate | Share the hand-off package (model card, contract, scorer, tests) and record their result in the cross-track record | Pending
I-11 | No Week 5 baseline model exists in this project line, so the baseline is naive (prior probability, single-rule score) | Low | Model comparison | Documented | Data Science | Naive baselines are the strictest available comparison | n/a

## Cross-track record
Field | Record
1. Track collaborated with | ML Engineering (hand-off prepared by Data Science; teammate review pending). Supporting inputs: Data Analytics (Week 6 EDA/statistical findings reused in feature review); Project Management (issue log).
2. Project dependency | ML Engineering depends on a model with documented inputs, outputs and limits; Data Science depends on ML Engineering to confirm the pipeline preserves them.
3. Component/output being tested | Scoring interface around the Week 6 candidate model: input contract, validation, output schema, persistence, speed.
4. Information/output received | [To complete with ML Engineering teammate: pipeline/preprocessing details, their input format, their run results]
5. Information/output provided | Model card, input/output contract (JSON), validated scorer (admission_risk_scorer.py), saved model, 18-case interface test suite, accepted/rejected-input rules, caution that the model has no predictive skill.
6. Testing activity completed | 18 interface test cases run on the Week 6 behaviour (V1) and the refined scorer (V2): V1 8/18, V2 18/18. [Teammate run: to be completed]
7. Issue/finding identified | 10 failures in V1: impossible/missing values scored silently, 'None'→NaN pitfall, unreported extra columns (possible identifiers), bare-array output, empty input crash, unclear error messages.
8. Refinement/action taken | Input contract with ranges and closed lists; validation with field-named errors; unseen-category warnings; documented output schema with version and 'use caution' field; empty-input handling.
9. Retest result | V2 passes 18/18 (src/admission_risk_scorer.py; outputs/tables/t_scoring_interface_tests.csv).
10. What changed as a result | Scores can no longer be produced from invalid input without a clear error or warning; the pipeline owner now has an explicit contract and a caution flag.
11. Evidence | Notebook section F; Figure W08; model_card.md; input_output_contract.json; models/admission_scorer_v2.joblib; [teammate confirmation/screenshot: to be added]
12. How it improved HealthConnect | Prevents silent bad scores and identifier leakage into the model pipeline, and makes the model's lack of skill visible to downstream users before Week 8 integration.

## Acceptance criteria
Criterion | Candidate (Week 6) | Refined (R1 Clinical-core features)
C1 AUC ≥ 0.65 | 0.529 [FAIL] | 0.537 [FAIL]
C2 CI lower > 0.5 | 0.470 [FAIL] | 0.485 [FAIL]
C3 PR-AUC ≥ 1.5×prevalence | 0.145 vs 0.176 [FAIL] | 0.145 vs 0.176 [FAIL]
C4 stable (≥90% splits >0.5 and time-split CI lower >0.5) | 40% / 0.43 [FAIL] | 63% / 0.44 [FAIL]
C5 slope 0.8–1.2 | 0.18 [FAIL] | 0.24 [FAIL]
C6 beats baseline (corrected CI of AUC−0.5 excludes 0) | -0.044 to +0.007 [FAIL] | -0.022 to +0.024 [FAIL]

## Interface tests
ID | Scenario | Expected | V1_Actual | V1 | V2_Actual | V2
X01 | Valid single record | Returns one probability in [0, 1] | scored, p=0.089 | PASS | scored, p=0.089 | PASS
X02 | Valid batch of 200 | 200 finite probabilities | 200 finite scores | PASS | 200 finite scores | PASS
X03 | Columns in a different order | Identical scores (columns matched by name) | identical scores | PASS | identical scores | PASS
X04 | Unexpected extra column (e.g. PatientName) | Scored; ignored column reported (identifier safety) | scored silently; extra column (possible identifier) not reported | FAIL | scored and extra column reported | PASS
X05 | Required column missing (Age) | Clear error naming 'Age' | ValueError: columns are missing: {'Age'} | PASS | ScoringError: Missing required column(s): ['Age'] | PASS
X06 | Unseen category in an open field (Occupation = Astronaut) | Scored, and the unseen value is reported | scored silently; unseen category not reported | FAIL | scored with warning | PASS
X07 | Impossible value in a closed list (ProvinceName = Mars) | Rejected with an error naming ProvinceName | scored an impossible province without complaint | FAIL | ScoringError: Column 'ProvinceName' has value(s) outside the allowed list ['Eastern', 'Kigali City', 'Northern | PASS
X08 | Out-of-range numbers (Age = -5, BMI = 500) | Rejected with an error naming the column | scored Age=-5, BMI=500 without complaint | FAIL | ScoringError: Column 'Age' out of allowed range [0, 110] at row(s) [0] | PASS
X09 | Missing numeric value (Age = NaN) | Clear error naming 'Age' | ValueError: Input X contains NaN. LogisticRegression does not accept missing values encoded as NaN natively. F | FAIL | ScoringError: Column 'Age' has missing value(s) at row(s) [0]; missing values are not imputed | PASS
X10 | Wrong data type (Age = 'forty') | Clear error naming 'Age' | ValueError: could not convert string to float: 'forty' | FAIL | ScoringError: Column 'Age' must be numeric; non-numeric value(s) at row(s) [0] | PASS
X11 | Empty input (0 rows) | Empty result, no crash | ValueError: Found array with 0 sample(s) (shape=(0, 7)) while a minimum of 1 is required by StandardScaler. | FAIL | empty result | PASS
X12 | Determinism (same input twice) | Identical output | identical on repeat | PASS | identical on repeat | PASS
X13 | Persistence (save and reload the scorer) | Identical output after reload | identical after save/load | PASS | identical after save/load | PASS
X14 | ChronicCondition = 'None' (valid: no chronic disease) | Accepted as a normal value | 'None' accepted as a value | PASS | 'None' accepted as a value | PASS
X15 | ChronicCondition missing — the CSV 'None'→NaN pitfall | Rejected with a clear error naming ChronicCondition | TypeError: ufunc 'isnan' not supported for the input types, and the inputs could not be safely coerced to any supported | FAIL | ScoringError: Column 'ChronicCondition' has missing value(s) at row(s) [0] - if the data came from a CSV, the text 'None | PASS
X16 | Output schema | risk_score, risk_band, warnings, model_version, use_caution | bare array: no band, warnings, version or caution flag | FAIL | output schema as documented | PASS
X17 | Input is not a DataFrame | Clear error saying a DataFrame is required | ValueError: Expected 2D array, got scalar array instead: array={'Age': 12, 'BMI': 43.3, 'RiskScore': 2, 'Docto | FAIL | ScoringError: Input must be a pandas DataFrame with one row per appointment. | PASS
X18 | Speed: 10,000 rows | Under 5 seconds | 10,000 rows in 0.02s | PASS | 10,000 rows in 0.02s | PASS