Week 7 Project Summary

Data Science track — complements (does not repeat) the Model Testing & Refinement Report

HealthConnect Clinic Experience Lab · AnalystLab Africa Experience Lab, Week 7 · Data Science track · Testing, Refinement & End-to-End Validation

| Item | Summary |
| --- | --- |
| 1. What I planned to test | The Week 6 candidate admission classifier (stability, metrics, calibration, errors, segments, overfitting, feature validity) and its scoring interface for ML Engineering. |
| 2. What I actually tested | 33 recorded tests: 15 model tests and 18 interface tests, against six acceptance criteria fixed in advance; hold-out opened once. |
| 3. Most important results | Hold-out AUC 0.529 (CI 0.47–0.59); 0 of 6 criteria met; calibration slope 0.18; planted signals ≥ AUC 0.57 are detectable, so the result is a data finding. |
| 4. Issues or weaknesses | No predictive skill; flags driven by noise categories; uninformative probabilities; silent acceptance of invalid inputs; CSV 'None'→NaN pitfall; look-ahead in PatientVisits; no attendance field in the data. |
| 5. Improvements made | Seven model refinements tried (none accepted); scoring interface rebuilt with an input/output contract, validation, output schema, model card and 'use caution' flag. |
| 6. Retesting results | Model: hold-out Δ AUC +0.008 (CI -0.04 to +0.06), still 0/6 criteria. Interface: 8/18 → 18/18 pass. |
| 7. Tracks collaborated with | ML Engineering (hand-off prepared; teammate sign-off pending); Data Analytics findings reused; Project Management issue log. |
| 8. What was tested collaboratively | Model scoring interface: valid, invalid, missing, out-of-range, unseen and empty inputs; output schema; persistence; speed. |
| 9. What changed as a result | Invalid input now produces a clear, field-named error or warning; outputs carry a version and a caution flag; identifiers in extra columns are reported. |
| 10. Key findings / validation outcomes | The model is not suitable for patient-level use; the test harness itself is validated (negative control and planted-signal power test) and reusable. |
| 11. Major challenges | Brief assumes a no-show dataset the project does not have; no signal in the data; Jupyter/statsmodels not installable in the working environment. |
| 12. Important decisions made | Test the Week 6 admission model rather than switch dataset (per the brief); pre-register criteria; reject refinements that do not clear +0.02 AUC with a significant corrected test; keep the model as a fixture only. |
| 13. Remaining limitations | One year of data; 586 admissions; inconsistent source keys; interface tests not yet verified by the ML Engineering teammate. |
| 14. Remaining issues / dependencies | I-01 (no skill), I-02 (attendance data source), I-05 (look-ahead feature), I-07 (probabilities), I-08 (source keys), I-10 (teammate sign-off) — see issue log. |
| 15. Contribution to HealthConnect | An evidence-based decision that avoids a misleading model, a validated and reusable testing harness, and a documented scoring component ready for pipeline integration. |
| 16. To complete before Week 8 | Obtain the attendance dataset (or confirm the proxy), re-run the harness on that target, complete the teammate's hand-off test, drop model risk percentages from any user-facing output, commit and present. |